## Executive Summary
ENGINEERING & MAINTENANCE DEPARTMENT — ONGOING WORKS SUMMARY
Executive Project Status Dashboard ¦ Automated Status Consolidation
Department / Project Line | Total Tasks | Completed | In Progress | Under Review | Pending / Scheduled | % Completed
Fiber Bleaching Line | 6 | 0 | 0 | 0 | 6 | 0%
R-Cot Department | 8 | 0 | 5 | 2 | 1 | 0%
Spunlace Project | 9 | 3 | 2 | 1 | 3 | 33.33%
TOTAL DEPARTMENTAL TASKS | 23 | 3 | 7 | 3 | 10 | 13.04%
STATUS COLOR CODE & WORKFLOW DEFINITION
Completed | Task fully executed, approved, or officially established.
In Progress | Currently active (drawings, fabrication, quotation review, or civil execution).
Scheduled | Confirmed upcoming milestone or stakeholder meeting scheduled.
Under Review | Awaiting management review, feasibility sign-off, or budget approval.
Pending | Awaiting prerequisites, shutdown schedule, or formal Purchase Order issuance.

## Fiber Bleaching
FIBER BLEACHING CAPACITY EXTENSION (TARGET: 1,500 TONS)
Departmental Ongoing Engineering & Maintenance Works Tracker ¦ Dept Ref: DEPT-FB-1500 ¦ Status as of: October 2026
Sr. # | Focus Area / Machine | Scope of Work / Action Item | Current Status | Action Owner / Department | Key Technical Remarks & Next Steps
1 | Pre-Blowroom Modification | Piping & ducting fabrication and line routing | Pending | Mechanical Maintenance | Work not initiated; pending line layout finalization and approved drawings.
2 | Pre-Blowroom Modification | Procurement of transport fan and material distributor | Pending | Procurement / Maintenance | Technical drawings shared; detailed review completed with Mr. Riyaz & engineering team.
3 | Post-Blowroom Modification | Piping & ducting fabrication and rerouting | Pending | Mechanical Maintenance | Scope of work defined; execution planned during the next scheduled plant shutdown.
4 | Post-Blowroom Modification | Procurement of transport fan and material distributor | Pending | Procurement | Equipment specifications verified; Purchase Requisition (PR) to be released.
5 | Dryer Unit Modification | Dryer overhaul & procurement of additional chamber | Pending | Project Engineering | Evaluating necessary component specifications and procurement in progress with Galvano.
6 | Post Line 2 Extension | Procurement & integration of new Multi-Mixer unit | Pending | Top Management / Maintenance | Under active internal technical and Capex evaluation for line expansion.

## R-Cot Line
R-COT DEPARTMENT UPGRADES & INSTALLATIONS
Departmental Ongoing Engineering & Maintenance Works Tracker ¦ Dept Ref: DEPT-RCOT-01 ¦ Status as of: October 2026
Sr. # | Equipment / System | Scope of Work / Action Item | Current Status | Action Owner / Department | Key Technical Remarks & Next Steps
1 | Bale Press | Procurement of new hydraulic bale press unit | In Progress | Procurement / Maintenance | Commercial quotations received from vendors; currently under technical & pricing evaluation.
2 | Automatic Bale Plucker | Procurement of new automatic bale plucker | Under Review | Project Engineering | Technical specifications finalized; awaiting vendor bid comparisons.
3 | Argus Fire Detection | Procurement & integration of spark/fire detectors | Under Review | EHS / Maintenance | Safety Capex evaluation initiated to integrate with existing blowroom safety loop.
4 | Filtration System | Installation and duct hookup of new filter unit | In Progress | Purchase / Mechanical | E-CAPEX approved; purchase order execution currently in Purchase Department.
5 | Ducting & Piping Works | Pneumatic transport & exhaust ducting fabrication | In Progress | Mechanical / Fabrication | E-CAPEX approved; material indentation in progress with local fabrication team.
6 | Power Infrastructure | Main incoming & motor feeder cable procurement | In Progress | Electrical Maintenance | E-CAPEX approved; cable schedule prepared, procurement approval in progress.
7 | Cable try work | Overhead cable tray installation and routing | In Progress | Electrical Maintenance | Purchase Request (PR) officially submitted to Purchase Department.
8 | Machine Automation | PLC programming, drive configuration & commissioning | Pending | Automation / Electrical | Scheduled immediately following machine mechanical erection and electrical power-up.

## Spunlace Project
SPUNLACE PRODUCTION LINE PROJECT
Departmental Ongoing Engineering & Maintenance Works Tracker ¦ Dept Ref: PRJ-SPUNLACE-01 ¦ Status as of: October 2026
Sr. # | Project Deliverable / Area | Scope of Work / Action Item | Current Status | Action Owner / Department | Key Technical Remarks & Next Steps
1 | Spunlace Production Line 1 | E-CAPEX approval workflow | Completed | Finance / Management | E-CAPEX officially authorized and approved.
2 | Spunlace Production Line 1 | Letter of Credit (LC) opening & transmission | Completed | Commercial / Banking | LC established and in transit with foreign machinery manufacturers.
3 | Spunlace Production Line 1 | Machine code & ERP asset registration | Completed | IT / Finance / Maintenance | New machine codes opened and configured in management system.
4 | Spunlace Production Line 1 | Purchase Order (PO) issuance | Pending | Procurement | Draft PO under commercial terms review;
5 | Technical Due Diligence | Trützschler engineering checklist submission | In Progress | Engineering / Maintenance | Checklist to be formally finalized to Trützschler following final inputs from FND.
6 | Consultancy & Design | Coordination meeting with FND consultants | Scheduled | Project Management | Technical alignment session scheduled for tomorrow to finalize civil & electrical scopes.
7 | Civil / Site Preparation | Inly Yard Job Request Form (JRF) submission | Pending | Civil / Maintenance | Civil Job Request Form (JRF) being finalized for ground preparation.
8 | Civil / Site Preparation | Raw Material Warehouse JRF execution | In Progress | Civil Engineering | JRF active and in progress (floor elevation +2'-0" and roof waterproofing works).
9 | Spunlace Production Line 2 | Project feasibility and Capex justification | Under Review | Top Management | Long-term capacity expansion proposal under strategic discussion with Top Management.